## Lich du an
BANG KE HOACH DU AN - COURSEHUB ONLINE LEARNING MARKETPLACE
Du an: CourseHub - Online Learning Marketplace |  |  |  | Nguoi lap: Cao Chi Thien |  |  | Bat dau: 08/07/2026 |  |  | Ket thuc: 21/07/2026
ID | Giai doan | Ten cong viec | FR lien quan | Bat dau | Ket thuc | Ngay | Phu trach | Phoi hop | Phu thuoc | Trang thai | 08/07 T4 | 09/07 T5 | 10/07 T6 | 13/07 T2 | 14/07 T3 | 15/07 T4 | 16/07 T5 | 17/07 T6 | 20/07 T2 | 21/07 T3
I. KHOI TAO
P01 | I. KHOI TAO | Lap ke hoach tai lieu du an |  | 08/07/2026 | 08/07/2026 | 1d | Cao Chi Thien | Toan team |  | Done | X
P02 | I. KHOI TAO | Review va hoan thien SRS | FR-01 to FR-26 | 08/07/2026 | 08/07/2026 | 1d | Cao Chi Thien | Nguyen Van Minh |  | Done | X
P03 | I. KHOI TAO | Hoan thien Calendar Template-Technical Report |  | 09/07/2026 | 09/07/2026 | 1d | Cao Chi Thien | Toan team | P01,P02 | Done |  | X
II. THIET KE
D01 | II. THIET KE | Thiet ke kien truc he thong Modular Monolith |  | 10/07/2026 | 10/07/2026 | 1d | Nguyen Van Minh | Cao Chi Thien | P03 | Done |  |  | X
D02 | II. THIET KE | Thiet ke Database Schema 21 bang | DB Design Sec.8 | 10/07/2026 | 10/07/2026 | 1d | Le Hoang Nam | Nguyen Van Minh | D01 | Done |  |  | X
D03 | II. THIET KE | Thiet ke UI/UX Wireframe 14 man hinh | UI Sec.10 | 10/07/2026 | 10/07/2026 | 1d | Tran Thi Lan | Cao Chi Thien | P03 | Done |  |  | X
III. BACKEND
BE01 | III. BACKEND | Setup Spring Boot project cau hinh moi truong |  | 11/07/2026 | 11/07/2026 | 1d | Nguyen Van Minh | Le Hoang Nam | D01,D02 | Done
BE02 | III. BACKEND | FR-01: Authentication Module | FR-01 | 11/07/2026 | 11/07/2026 | 1d | Nguyen Van Minh |  | BE01 | Done
BE03 | III. BACKEND | FR-02 FR-03: User + Instructor Profile | FR-02, FR-03 | 11/07/2026 | 11/07/2026 | 1d | Nguyen Van Minh |  | BE02 | Done
BE04 | III. BACKEND | FR-04 FR-05 FR-06: Course + Category + Tag | FR-04,FR-05,FR-06 | 12/07/2026 | 13/07/2026 | 2d | Nguyen Van Minh | Le Hoang Nam | BE03 | Done |  |  |  | X
BE05 | III. BACKEND | FR-07 FR-08: Chapter + Lesson Management | FR-07,FR-08 | 12/07/2026 | 13/07/2026 | 2d | Nguyen Van Minh |  | BE04 | Done |  |  |  | X
BE06 | III. BACKEND | FR-09 FR-10: Video Processing + Document Resource | FR-09,FR-10 | 14/07/2026 | 14/07/2026 | 1d | Le Hoang Nam | Nguyen Van Minh | BE05 | Done |  |  |  |  | X
BE07 | III. BACKEND | FR-11: Quiz Module | FR-11 | 14/07/2026 | 14/07/2026 | 1d | Nguyen Van Minh |  | BE05 | Done |  |  |  |  | X
BE08 | III. BACKEND | FR-12 FR-13: Enrollment + Progress Tracking | FR-12,FR-13 | 14/07/2026 | 15/07/2026 | 2d | Nguyen Van Minh |  | BE06,BE07 | Done |  |  |  |  | X | X
BE09 | III. BACKEND | FR-14 FR-15: Review + Comment System | FR-14,FR-15 | 15/07/2026 | 15/07/2026 | 1d | Nguyen Van Minh |  | BE08 | Done | [5 empty] | X
BE10 | III. BACKEND | FR-18 FR-19: Notification + Certificate | FR-18,FR-19 | 15/07/2026 | 15/07/2026 | 1d | Nguyen Van Minh | Le Hoang Nam | BE08 | Done | [5 empty] | X
BE11 | III. BACKEND | FR-20 FR-21: Report + Admin Dashboard | FR-20,FR-21 | 15/07/2026 | 15/07/2026 | 1d | Nguyen Van Minh | Le Hoang Nam | BE09 | Done | [5 empty] | X
BE12 | III. BACKEND | FR-22 FR-23 FR-26: Dashboards + Statistics | FR-22,FR-23,FR-26 | 15/07/2026 | 15/07/2026 | 1d | Nguyen Van Minh |  | BE09,BE10,BE11 | Done | [5 empty] | X
BE13 | III. BACKEND | FR-24 FR-25: Full-Text Search + Multi-Filter | FR-24,FR-25 | 15/07/2026 | 15/07/2026 | 1d | Nguyen Van Minh |  | BE04 | Done | [5 empty] | X
BE14 | III. BACKEND | FR-16 FR-17: Favorite + Wishlist | FR-16,FR-17 | 15/07/2026 | 15/07/2026 | 1d | Nguyen Van Minh |  | BE08 | Done | [5 empty] | X
IV. FRONTEND
FE01 | IV. FRONTEND | Setup React Vite TypeScript project |  | 11/07/2026 | 11/07/2026 | 1d | Tran Thi Lan |  | D03 | Done
FE02 | IV. FRONTEND | Layout Header Footer Dark Mode Design System | UI Sec.10 | 11/07/2026 | 11/07/2026 | 1d | Tran Thi Lan |  | FE01 | Done
FE03 | IV. FRONTEND | Login Register OTP Forgot Password pages | FR-01 | 12/07/2026 | 12/07/2026 | 1d | Tran Thi Lan |  | FE02 | Done
FE04 | IV. FRONTEND | Home Page + Course Listing Search Filter | FR-24,FR-25 | 12/07/2026 | 13/07/2026 | 2d | Tran Thi Lan |  | FE02 | Done |  |  |  | X
FE05 | IV. FRONTEND | Course Detail Page | FR-04,FR-14 | 13/07/2026 | 13/07/2026 | 1d | Tran Thi Lan |  | FE04 | Done |  |  |  | X
FE06 | IV. FRONTEND | Learning Page Video PDF Quiz Text | FR-11,FR-12,FR-13,FR-15 | 14/07/2026 | 15/07/2026 | 2d | Tran Thi Lan |  | FE05 | Done |  |  |  |  | X | X
FE07 | IV. FRONTEND | Student Dashboard My Courses Certificates History | FR-19,FR-23 | 15/07/2026 | 15/07/2026 | 1d | Tran Thi Lan |  | FE06 | Done | [5 empty] | X
FE08 | IV. FRONTEND | Instructor Dashboard + Course Builder | FR-04,FR-07,FR-08,FR-09,FR-22 | 15/07/2026 | 16/07/2026 | 2d | Tran Thi Lan |  | FE07 | Done | [5 empty] | X | X
FE09 | IV. FRONTEND | Admin Dashboard Approve Users Reports Categories | FR-05,FR-06,FR-20,FR-21 | 16/07/2026 | 16/07/2026 | 1d | Tran Thi Lan |  | FE08 | Done | [6 empty] | X
FE10 | IV. FRONTEND | Profile Page Notification Certificate Verify | FR-02,FR-18,FR-19 | 16/07/2026 | 16/07/2026 | 1d | Tran Thi Lan |  | FE07 | Done | [6 empty] | X
V. TICH HOP
INT01 | V. TICH HOP | Tich hop Frontend Backend API | All FRs | 16/07/2026 | 17/07/2026 | 2d | Tran Thi Lan | Nguyen Van Minh | BE13,FE09 | Done | [6 empty] | X | X
INT02 | V. TICH HOP | Tich hop AWS S3 + CloudFront CDN | FR-09,FR-10 | 17/07/2026 | 17/07/2026 | 1d | Le Hoang Nam | Nguyen Van Minh | BE06 | Done | [7 empty] | X
INT03 | V. TICH HOP | Tich hop Email Service + WebSocket Notification | FR-18 | 17/07/2026 | 17/07/2026 | 1d | Le Hoang Nam | Nguyen Van Minh | BE10 | Done | [7 empty] | X
VI. KIEM THU
QA01 | VI. KIEM THU | Lap Test Plan + Test Cases 26 FRs | All FRs | 17/07/2026 | 17/07/2026 | 1d | Pham Thu Ha | Cao Chi Thien | INT01 | Done | [7 empty] | X
QA02 | VI. KIEM THU | API Testing Postman Newman | FR-01 to FR-26 | 17/07/2026 | 18/07/2026 | 2d | Pham Thu Ha | Nguyen Van Minh | QA01 | Done | [7 empty] | X
QA03 | VI. KIEM THU | Integration UI Testing end-to-end flows | Business Flows | 18/07/2026 | 18/07/2026 | 1d | Pham Thu Ha | Tran Thi Lan | QA02 | Done
QA04 | VI. KIEM THU | Security + Performance Testing | NFR Security Sec.12 | 18/07/2026 | 18/07/2026 | 1d | Pham Thu Ha | Le Hoang Nam | QA02 | Done
VII. TRIEN KHAI
DEP01 | VII. TRIEN KHAI | Cau hinh Docker moi truong Production |  | 18/07/2026 | 18/07/2026 | 1d | Le Hoang Nam |  | QA02 | Done
DEP02 | VII. TRIEN KHAI | Deploy Backend + Database len server |  | 18/07/2026 | 19/07/2026 | 2d | Le Hoang Nam | Nguyen Van Minh | DEP01 | Done
DEP03 | VII. TRIEN KHAI | Deploy Frontend + cau hinh CDN |  | 19/07/2026 | 19/07/2026 | 1d | Le Hoang Nam | Tran Thi Lan | DEP02 | Done
VIII. KET THUC
UAT01 | VIII. KET THUC | User Acceptance Testing UAT | All FRs | 20/07/2026 | 20/07/2026 | 1d | Pham Thu Ha | Cao Chi Thien | DEP03 | Done | [8 empty] | X
UAT02 | VIII. KET THUC | Bug Fix sau UAT |  | 20/07/2026 | 21/07/2026 | 2d | Nguyen Van Minh | Tran Thi Lan, Pham Thu Ha | UAT01 | Done | [8 empty] | X | X
CL01 | VIII. KET THUC | Hoan thien tai lieu cuoi du an |  | 21/07/2026 | 21/07/2026 | 1d | Cao Chi Thien | Toan team | UAT02 | Done | [9 empty] | X
CL02 | VIII. KET THUC | Nghiem thu va Ban giao du an |  | 21/07/2026 | 21/07/2026 | 1d | Cao Chi Thien | Toan team | CL01 | Done | [9 empty] | X
X = Ngay lam viec cua task ¦ Mau = Giai doan ¦ Thu 7 Chu nhat: nghi