BAO CAO TONG KET DU AN

COURSEHUB - ONLINE LEARNING MARKETPLACE

Phien ban: 1.0  |  Ngay lap: 08/07/2026

Nguoi lap: Cao Chi Thien

Vai tro: Project Manager / Business Analyst

1. TONG QUAN DU AN

| Thong tin | Chi tiet |
| --- | --- |
| Ten du an | CourseHub - Online Learning Marketplace |
| Loai du an | Phan mem Web - E-Learning Marketplace Platform |
| Nguoi lap ke hoach | Cao Chi Thien (Project Manager / Business Analyst) |
| Ngay bat dau du an | 08/07/2026 (Khoi tao tai lieu + Review SRS) |
| Ngay ket thuc du an | 21/07/2026 (Nghiem thu + Ban giao) |
| Thoi gian thuc hien | 14 ngay duong lich ¦ 10 ngay lam viec (khong tinh T7 CN) |
| Giai doan tai lieu | 08/07/2026 - 09/07/2026 |
| Giai doan trien khai | 10/07/2026 - 21/07/2026 |
| Tong ngan sach du kien | 68,190,625 VND (~$2,728 USD) |
| Quy mo team | 5 thanh vien (PM, Backend Dev, Frontend Dev, DB/DevOps, QA) |
| So module chuc nang | 26 Functional Requirements (FR-01 den FR-26) |
| Tieu chuan tai lieu SRS | IEEE 830 / IEEE 29148 |

2. GIOI THIEU HE THONG

CourseHub la mot nen tang Marketplace hoc truc tuyen da chieu, ket hop tinh nang cua ca Learning Management System (LMS) truyen thong va san giao dich khoa hoc mo (tuong tu Udemy, Coursera). He thong duoc xay dung theo kien truc Modular Monolith voi Backend Spring Boot Java 17 va Frontend React TypeScript, san sang chuyen doi Microservices khi can.

2.1 Cac nhom nguoi dung - Actors (Theo SRS Section 2.3)

| Actor | Mo ta chi tiet |
| --- | --- |
| Guest (Khach vang lai) | Chua dang nhap. Xem danh sach, tim kiem khoa hoc, xem trang chi tiet, xem thu bai hoc co isPreview=true. |
| Student (Hoc vien) | Da dang nhap. Dang ky hoc free/paid, theo doi tien do, lam Quiz, tai PDF, viet danh gia, binh luan, nhan chung chi PDF tu dong. |
| Instructor (Giang vien) | Account Student da kich hoat Instructor role. Tao khoa hoc, upload video HLS, gui duyet Admin, quan ly Dashboard doanh thu. |
| Admin (Quan tri vien) | Nhan su he thong. Duyet/tu choi khoa hoc, ban/unban User, quan ly danh muc/tag, xu ly bao cao vi pham, xem thong ke he thong. |

3. MUC TIEU DU AN

- Xay dung nen tang Marketplace hoc truc tuyen dang tin cay (Udemy cua Viet Nam).

- Ho tro day du 4 nhom nguoi dung: Guest, Student, Instructor, Admin.

- Trien khai 26 module chuc nang theo SRS (FR-01 den FR-26).

- Dam bao kien truc Modular Monolith san sang chuyen doi Microservices.

- Video streaming HLS/DASH qua CDN, chong tai lau bang AWS Signed URLs.

- He thong danh gia chong review ao (>= 30pct progress hoac >= 3 ngay sau enroll).

- JWT + Refresh Token Rotation (RTR) bao mat cao, RBAC phan quyen 3 vai tro.

- Cap chung chi so tu dong (PDF + UUID code) khi hoan thanh 100pct khoa hoc.

- Hoan thanh dung tien do: 08/07/2026 - 21/07/2026.

4. PHAM VI DU AN

4.1 Pham vi trong du an - In-Scope (26 Functional Requirements)

| FR ID | Ten module | Mo ta ngan gon |
| --- | --- | --- |
| FR-01 | Authentication | Register/Login JWT HS256, OTP Email, Refresh Token Rotation, Forgot Password, BCrypt pw12 |
| FR-02 | User Profile | Update profile avatar bio phone, change password |
| FR-03 | Instructor Profile | Become Instructor request, Multi-role Switch Student <-> Instructor |
| FR-04 | Course Management | CRUD khoa hoc, Approval Workflow DRAFT->PENDING->PUBLISHED->ARCHIVED->BLOCKED |
| FR-05 | Category Management | Phan cap 3 cap Grandparent->Parent->Child, self-referencing |
| FR-06 | Tag Management | Gan tag cho khoa hoc, Admin quan ly tag |
| FR-07 | Chapter Management | CRUD chuong hoc, order_index, drag-drop reorder |
| FR-08 | Lesson Management | VIDEO/PDF/TEXT, isPreview config, order_index, duration |
| FR-09 | Video Processing | S3 Presigned URL, FFmpeg HLS 360p/480p/720p/1080p, Redis Queue async |
| FR-10 | Document PDF | PDF upload S3, Rich Text content jsoup XSS sanitize, is_downloadable |
| FR-11 | Quiz | Single/Multiple Choice, True/False, Passing Score, Shuffle questions/options, Import Excel |
| FR-12 | Enrollment | Dang ky hoc ACTIVE/COMPLETED/REFUNDED, composite unique user+course |
| FR-13 | Progress Tracking | >=90pct video time-watched auto-complete, pct total course, lesson-level progress |
| FR-14 | Conditional Review | >=30pct progress OR >=3 days after enroll, 1 review/course/student, anti-fake |
| FR-15 | Comment Q&A | Threaded/Nested comments parent_id, Instructor label, CRUD by owner/Admin |
| FR-16 | Favorite | Toggle heart icon, user_favorites N-N, list my favorites paginated |
| FR-17 | Wishlist | Add/remove, auto-remove when enrolled, wishlists list |
| FR-18 | Notification | WebSocket/SSE in-app real-time, Email async queue, mark-read, mark-all-read |
| FR-19 | Certificate | PDF auto generated UUID code, S3 storage, /verify-certificate public endpoint |
| FR-20 | Report Content | Polymorphic reportable_type Course/Comment/User, PENDING/RESOLVED/DISMISSED |
| FR-21 | Admin Dashboard | Course approval queue, User ban/unban, Report handling, System stats MAU CCU |
| FR-22 | Instructor Dashboard | Revenue stats, Enrollment chart ChartJS, Q&A panel |
| FR-23 | Student Dashboard | My Courses grid progress bars, Certificates tab, Purchase history |
| FR-24 | Full-Text Search | PostgreSQL tsvector Full-Text Search, keyword highlight, ranked results |
| FR-25 | Multi-Filter | Rating/Level/Price/Sort Dynamic Specifications, AJAX pagination Pageable |
| FR-26 | Statistics Report | Analytics dashboard Admin, Export Excel/CSV report |

4.2 Pham vi ngoai du an - Out-Scope

- Thanh toan thuc te Stripe/PayPal Production (chi cau truc du lieu san sang).

- AI Quiz Generator, AI Chatbot, Recommendation Engine nang cao.

- Mobile App iOS/Android.

- B2B Subscription Package.

- Blockchain Certificate Verification.

- Multi-language i18n (chi tieng Viet).

5. KIEN TRUC HE THONG

He thong CourseHub su dung kien truc Modular Monolith (Single Deployable Unit), duoc thiet ke san sang de tach ra thanh Microservices khi quy mo lon hon.

5.1 Cac tang kien truc (Theo SRS Section 2.1, 2.4)

| Tang | Cong nghe | Chuc nang |
| --- | --- | --- |
| Client Layer | React 18 + TypeScript + Vite | SPA, React Router v6, Redux Toolkit, Axios |
| API Gateway | Nginx reverse proxy | HTTPS/TLS, CORS, Load Balancing, Rate Limiting |
| Application Layer | Spring Boot 3.x Java 17 | REST API, Business Logic, JWT Security, RBAC |
| Cache Layer | Redis 7.0+ | Session, OTP TTL, Rate limit counter, Task queue video processing |
| Database Layer | PostgreSQL 15+ | 21 bang du lieu chinh, Full-Text Search tsvector |
| Storage Layer | AWS S3 + CloudFront CDN | Video HLS files, PDF resources, Certificate PDF |
| Processing Layer | FFmpeg Worker Docker | Video Transcoding m3u8, .ts segments, multi-quality |
| Email Layer | AWS SES / Sendgrid | OTP email, Notification email, Certificate email |

5.2 Database Entities - 21 bang (Theo SRS Section 8)

| Bang du lieu | Mo ta |
| --- | --- |
| users | UUID PK, email unique, bcrypt_hash, status (ACTIVE/INACTIVE/BANNED), soft delete |
| roles | ROLE_STUDENT, ROLE_INSTRUCTOR, ROLE_ADMIN |
| user_roles | N-N bridge: User <-> Role (multi-role Switch support) |
| courses | UUID PK, instructor_id FK, category_id FK, status lifecycle, level, price |
| categories | Phan cap 3 cap, self-referencing parent_id nullable |
| tags + course_tags | Tag entity va N-N bridge voi courses |
| chapters | course_id FK, title, order_index, is_published |
| lessons | chapter_id FK, lesson_type (VIDEO/PDF/TEXT), isPreview, order_index, duration |
| lesson_resources | lesson_id FK, S3 URL, duration_seconds, text_content, is_downloadable |
| enrollments | user_id+course_id unique, progress_percent, status, enrolled_at |
| progress | enrollment_id FK, lesson_id FK, is_completed, watched_seconds |
| reviews | enrollment_id unique, rating 1-5, comment, is_visible |
| comments | lesson_id FK, user_id FK, parent_id nullable (threaded), content |
| certificates | user_id+course_id unique, certificate_code UUID, pdf_url S3, issued_at |
| notifications | recipient_id FK, type, title, message, is_read, target_url |
| reports | Polymorphic: reportable_type (Course/Comment/User), reportable_id, reason, status |
| course_approval_history | course_id FK, reviewer_id FK, action (SUBMIT/APPROVE/REJECT), note |
| refresh_tokens | user_id FK, token hash, expiry_date, revoked (RTR pattern) |
| instructor_followers | follower_id FK, instructor_id FK |
| orders + order_items | Don hang thanh toan cau truc, san sang tich hop payment gateway |
| coupons + instructor_payouts | Ma giam gia va doi soat thu nhap Instructor |

6. CONG NGHE SU DUNG (Theo SRS Section 2.1)

| Phan loai | Cong nghe chi tiet |
| --- | --- |
| Backend | Java 17, Spring Boot 3.x, Spring Security 6, JWT HS256, Spring Data JPA, Hibernate Validator, Bucket4j Rate Limiting, jsoup XSS |
| Frontend | React 18, TypeScript, Vite build tool, Redux Toolkit, React Router v6, Axios, hls.js, ChartJS/Recharts |
| Database | PostgreSQL 15+ (relational main DB, Full-Text Search tsvector), Redis 7.0+ (cache/session/queue/rate-limit) |
| Cloud/Storage | AWS S3 (video/PDF/certificate), AWS CloudFront CDN (HLS streaming), AWS SES (email) |
| Video Processing | FFmpeg transcoding: 360p/480p/720p/1080p, HLS m3u8 playlist, .ts segments, Redis Queue async |
| Security | BCrypt work factor 12, JWT HS256 RTR, RBAC 3 roles, CORS whitelist, HTTPS/TLS 1.3, AWS Signed URLs |
| DevOps | Docker + docker-compose, Ubuntu Server 22.04 LTS, Nginx reverse proxy |
| Testing | JUnit 5, Mockito, Postman/Newman API testing, Manual UAT Testing |

7. KE HOACH THUC HIEN (Tu 08/07/2026 den 21/07/2026)

| Task ID | Giai doan | Ten cong viec | Bat dau | Ket thuc | Phu trach | Trang thai |
| --- | --- | --- | --- | --- | --- | --- |
| P01 | I. KHOI TAO | Lap ke hoach tai lieu du an | 08/07/2026 | 08/07/2026 | Cao Chi Thien | Done |
| P02 |  | Review va hoan thien SRS | 08/07/2026 | 08/07/2026 | Cao Chi Thien | Done |
| P03 |  | Hoan thien Calendar Template-Technical Report | 09/07/2026 | 09/07/2026 | Cao Chi Thien | Done |
| D01 | II. THIET KE | Thiet ke kien truc he thong Modular Monolith | 10/07/2026 | 10/07/2026 | Nguyen Van Minh | Done |
| D02 |  | Thiet ke Database Schema 21 bang | 10/07/2026 | 10/07/2026 | Le Hoang Nam | Done |
| D03 |  | Thiet ke UI/UX Wireframe 14 man hinh | 10/07/2026 | 10/07/2026 | Tran Thi Lan | Done |
| BE01 | III. BACKEND | Setup Spring Boot project cau hinh moi truong | 11/07/2026 | 11/07/2026 | Nguyen Van Minh | Done |
| BE02 |  | FR-01: Authentication Module | 11/07/2026 | 11/07/2026 | Nguyen Van Minh | Done |
| BE03 |  | FR-02 FR-03: User + Instructor Profile | 11/07/2026 | 11/07/2026 | Nguyen Van Minh | Done |
| BE04 |  | FR-04 FR-05 FR-06: Course + Category + Tag | 12/07/2026 | 13/07/2026 | Nguyen Van Minh | Done |
| BE05 |  | FR-07 FR-08: Chapter + Lesson Management | 12/07/2026 | 13/07/2026 | Nguyen Van Minh | Done |
| BE06 |  | FR-09 FR-10: Video Processing + Document Resource | 14/07/2026 | 14/07/2026 | Le Hoang Nam | Done |
| BE07 |  | FR-11: Quiz Module | 14/07/2026 | 14/07/2026 | Nguyen Van Minh | Done |
| BE08 |  | FR-12 FR-13: Enrollment + Progress Tracking | 14/07/2026 | 15/07/2026 | Nguyen Van Minh | Done |
| BE09 |  | FR-14 FR-15: Review + Comment System | 15/07/2026 | 15/07/2026 | Nguyen Van Minh | Done |
| BE10 |  | FR-18 FR-19: Notification + Certificate | 15/07/2026 | 15/07/2026 | Nguyen Van Minh | Done |
| BE11 |  | FR-20 FR-21: Report + Admin Dashboard | 15/07/2026 | 15/07/2026 | Nguyen Van Minh | Done |
| BE12 |  | FR-22 FR-23 FR-26: Dashboards + Statistics | 15/07/2026 | 15/07/2026 | Nguyen Van Minh | Done |
| BE13 |  | FR-24 FR-25: Full-Text Search + Multi-Filter | 15/07/2026 | 15/07/2026 | Nguyen Van Minh | Done |
| BE14 |  | FR-16 FR-17: Favorite + Wishlist | 15/07/2026 | 15/07/2026 | Nguyen Van Minh | Done |
| FE01 | IV. FRONTEND | Setup React Vite TypeScript project | 11/07/2026 | 11/07/2026 | Tran Thi Lan | Done |
| FE02 |  | Layout Header Footer Dark Mode Design System | 11/07/2026 | 11/07/2026 | Tran Thi Lan | Done |
| FE03 |  | Login Register OTP Forgot Password pages | 12/07/2026 | 12/07/2026 | Tran Thi Lan | Done |
| FE04 |  | Home Page + Course Listing Search Filter | 12/07/2026 | 13/07/2026 | Tran Thi Lan | Done |
| FE05 |  | Course Detail Page | 13/07/2026 | 13/07/2026 | Tran Thi Lan | Done |
| FE06 |  | Learning Page Video PDF Quiz Text | 14/07/2026 | 15/07/2026 | Tran Thi Lan | Done |
| FE07 |  | Student Dashboard My Courses Certificates History | 15/07/2026 | 15/07/2026 | Tran Thi Lan | Done |
| FE08 |  | Instructor Dashboard + Course Builder | 15/07/2026 | 16/07/2026 | Tran Thi Lan | Done |
| FE09 |  | Admin Dashboard Approve Users Reports Categories | 16/07/2026 | 16/07/2026 | Tran Thi Lan | Done |
| FE10 |  | Profile Page Notification Certificate Verify | 16/07/2026 | 16/07/2026 | Tran Thi Lan | Done |
| INT01 | V. TICH HOP | Tich hop Frontend Backend API | 16/07/2026 | 17/07/2026 | Tran Thi Lan | Done |
| INT02 |  | Tich hop AWS S3 + CloudFront CDN | 17/07/2026 | 17/07/2026 | Le Hoang Nam | Done |
| INT03 |  | Tich hop Email Service + WebSocket Notification | 17/07/2026 | 17/07/2026 | Le Hoang Nam | Done |
| QA01 | VI. KIEM THU | Lap Test Plan + Test Cases 26 FRs | 17/07/2026 | 17/07/2026 | Pham Thu Ha | Done |
| QA02 |  | API Testing Postman Newman | 17/07/2026 | 18/07/2026 | Pham Thu Ha | Done |
| QA03 |  | Integration UI Testing end-to-end flows | 18/07/2026 | 18/07/2026 | Pham Thu Ha | Done |
| QA04 |  | Security + Performance Testing | 18/07/2026 | 18/07/2026 | Pham Thu Ha | Done |
| DEP01 | VII. TRIEN KHAI | Cau hinh Docker moi truong Production | 18/07/2026 | 18/07/2026 | Le Hoang Nam | Done |
| DEP02 |  | Deploy Backend + Database len server | 18/07/2026 | 19/07/2026 | Le Hoang Nam | Done |
| DEP03 |  | Deploy Frontend + cau hinh CDN | 19/07/2026 | 19/07/2026 | Le Hoang Nam | Done |
| UAT01 | VIII. KET THUC | User Acceptance Testing UAT | 20/07/2026 | 20/07/2026 | Pham Thu Ha | Done |
| UAT02 |  | Bug Fix sau UAT | 20/07/2026 | 21/07/2026 | Nguyen Van Minh | Done |
| CL01 |  | Hoan thien tai lieu cuoi du an | 21/07/2026 | 21/07/2026 | Cao Chi Thien | Done |
| CL02 |  | Nghiem thu va Ban giao du an | 21/07/2026 | 21/07/2026 | Cao Chi Thien | Done |

8. NHAN SU DU AN

| STT | Ho ten | Vai tro | Ky nang chinh | Cong viec phu trach |
| --- | --- | --- | --- | --- |
| 1 | Cao Chi Thien | Project Manager / Business Analyst | Project Management, Business Analysis, SRS, Risk Management | Quan ly tien do, Phan tich yeu cau, Kiem soat SRS, Bao cao du an |
| 2 | Nguyen Van Minh | Senior Backend Developer | Java 17, Spring Boot 3.x, Spring Security, JWT, Redis, PostgreSQL | Authentication, Course API, Enrollment, Quiz, Notification Service |
| 3 | Tran Thi Lan | Frontend Developer | React 18, TypeScript, Vite, Redux, hls.js, ChartJS | UI/UX Components, Learning Page, Dashboard, Search Filter, Certificate |
| 4 | Le Hoang Nam | Database Engineer / DevOps | PostgreSQL 15, Redis 7, Docker, AWS S3, CloudFront, FFmpeg | Database Design, Schema Migration, AWS Integration, Deployment, DevOps |
| 5 | Pham Thu Ha | QA Engineer | Test Case Design, Postman Newman, Manual Testing, Bug Reporting | Test Plan, Test Cases, API Testing, UAT Execution, Bug Tracking |

9. NGAN SACH DU AN

| Hang muc | Noi dung chi tiet | Thanh tien (VND) |
| --- | --- | --- |
| Nhan su 5 nguoi x 2 tuan | PM/BA, Backend Dev, Frontend Dev, DB/DevOps, QA | 63,000,000 |
| Ha tang dam may AWS | EC2, RDS PostgreSQL, S3, CloudFront, Redis, Domain | 1,987,500 |
| Cong cu phat trien | IntelliJ IDEA, Figma Pro, AWS SES email service | 575,000 |
| Chi phi du phong 5 phan tram | Contingency cho rui ro phat sinh | 2,628,125 |
| TONG NGAN SACH DU KIEN |  | 68,190,625 |

Tong ngan sach du kien: 68,190,625 VND (~$2,728 USD)

Chi phi nhan su dua tren market rate cho du an phan mem quy mo nho tai Viet Nam. Ty gia: 1 USD = 25,000 VND.

10. QUAN LY RUI RO

| Ma RR | Muc do | Mo ta rui ro | Bien phap giam thieu |
| --- | --- | --- | --- |
| R01 | CAO | Tien do Backend cham do scope rong | Daily standup, uu tien MVP features truoc, scope-freeze sau 09/07 |
| R02 | TRUNG BINH | Loi tich hop FFmpeg Video Transcoding | Test pipeline rieng tren staging, fallback direct upload neu can |
| R03 | TRUNG BINH | AWS S3/CloudFront cau hinh sai | Test staging truoc production, follow AWS best practices checklist |
| R04 | CAO | CORS/Security misconfiguration | Security review rieng truoc UAT, pentest noi bo, soat code OWASP |
| R05 | THAP | Database schema conflict giua thanh vien | Flyway/Liquibase migration files, bat buoc code review DB changes |
| R06 | CAO | Timeline 2 tuan qua ngan cho scope lon | Scope-freeze ngay sau 09/07, khong them tinh nang ngoai SRS |
| R07 | THAP | AWS SES email delivery issues | Cau hinh Sendgrid backup, monitor bounce rate, warm-up IP sending |

11. KET QUA DU KIEN VA CHI SO THANH CONG

| Ma | Tai lieu / San pham ban giao | Mo ta | Ngay ban giao |
| --- | --- | --- | --- |
| D01 | Source code Backend Spring Boot | Java 17 application - GitHub repository, README.md | 21/07/2026 |
| D02 | Source code Frontend React | TypeScript + Vite - GitHub repository, README.md | 21/07/2026 |
| D03 | Database Schema + Migration | PostgreSQL 15 SQL scripts + Flyway migration files | 10/07/2026 |
| D04 | SRS Document | CourseHub_Final_SRS.docx theo chuan IEEE 830/29148 | 09/07/2026 |
| D05 | API Documentation | Swagger UI tu dong tu Spring Boot annotations + Postman Collection | 21/07/2026 |
| D06 | Project Management Docs | Calendar_CourseHub.xlsx, Template-Technical_CourseHub.xlsx, Report.docx | 09/07/2026 |
| D07 | Test Cases + Test Report | Test plan, Test cases cho 26 FRs, Newman HTML report | 18/07/2026 |
| D08 | Deployment Guide | Docker setup, AWS configuration, environment variables guide | 21/07/2026 |
| D09 | He thong hoat dong | Server production deploy thanh cong, uptime 99.9pct staging | 19/07/2026 |
| D10 | Bien ban nghiem thu | Ky bien ban nghiem thu ban giao toan bo du an | 21/07/2026 |

Chi so thanh cong (KPIs)

- 26/26 module chuc nang FR-01 den FR-26 duoc trien khai va test thanh cong.

- 100pct API endpoints pass automated testing Postman/Newman.

- Response time API GET < 200ms, POST/PUT < 500ms (theo NFR-11.1 trong SRS).

- Khong co loi Security Critical: SQL Injection, XSS, JWT bypass.

- Video HLS streaming on dinh cho 50 concurrent viewers.

- Certificate PDF tu dong cap khi Student hoan thanh 100pct khoa hoc.

- Hoan thanh dung timeline: 08/07/2026 - 21/07/2026.

PHU LUC A: NGUON DU LIEU (Nguon goc cua cac thong tin trong tai lieu nay)

| Loai thong tin | Nguon | Ghi chu |
| --- | --- | --- |
| Actors Guest/Student/Instructor/Admin | SRS Section 2.3 - Stakeholders | Truc tiep tu SRS |
| Functional Requirements FR-01 den FR-26 | SRS Section 4 - Functional Requirements | Truc tiep tu SRS |
| Database Design 21 bang | SRS Section 8 - Database Design | Truc tiep tu SRS |
| API Design 40+ endpoints | SRS Section 9 - API Specification | Truc tiep tu SRS |
| UI Specification 14 man hinh | SRS Section 10 - UI/UX Specification | Truc tiep tu SRS |
| Non-Functional Requirements | SRS Section 11 - NFRs | Truc tiep tu SRS |
| Security Requirements | SRS Section 12 - Security Requirements | Truc tiep tu SRS |
| Business Rules BR-001 den BR-010 | SRS Section 6 - Business Rules | Truc tiep tu SRS |
| Technology Stack | SRS Section 2.1 va 2.4 | Truc tiep tu SRS |
| Nhan su 5 thanh vien | Gia lap hop ly | Phu hop quy mo du an nho |
| Chi phi Ngan sach | Gia lap hop ly dua tren market rate VN | Ty gia 1 USD = 25,000 VND |
| Timeline 10 ngay lam viec | Gia lap hop ly dua tren scope SRS | 08/07 - 21/07/2026 |