## 1. Project Charter
PROJECT CHARTER - DU AN COURSEHUB ONLINE LEARNING MARKETPLACE
Ten du an: | CourseHub - Online Learning Marketplace
Don vi trien khai: | CourseHub Development Team
Giam doc / PM: | Cao Chi Thien
Quan tri du an: | Cao Chi Thien
Ngay bat dau: | 08/07/2026
Ngay ket thuc: | 21/07/2026
Phien ban: | v1.0
MUC TIEU DU AN
1. Xay dung nen tang Marketplace hoc truc tuyen CourseHub voi 26 module chuc nang theo SRS. 2. Phat trien he thong cho phep 4 nhom nguoi dung: Guest, Student, Instructor, Admin. 3. Backend Spring Boot Java 17 + Frontend React TypeScript + PostgreSQL + Redis. 4. JWT Auth, Video HLS Streaming, Quiz, Certificate PDF, Notification, Admin Dashboard. 5. Hoan thanh trong 2 tuan: 08/07/2026 - 21/07/2026.
PHAM VI DU AN - IN-SCOPE
FR-01: Authentication (Register/Login JWT/OTP/RTR/Forgot Password) FR-02: User Profile (avatar, bio, phone, change password) FR-03: Instructor Profile (Become Instructor, Multi-role Switch) FR-04: Course Management (DRAFT->PENDING->PUBLISHED Approval Workflow) FR-05: Category Management (3-level hierarchy Grandparent->Parent->Child) FR-06: Tag Management (Admin manage, assign to course) FR-07: Chapter Management (CRUD, order_index drag-drop) FR-08: Lesson Management (VIDEO/PDF/TEXT, isPreview config) FR-09: Video Processing (S3 Presigned URL, FFmpeg HLS 360p-1080p, Redis Queue) FR-10: Document PDF Resource (S3 upload, Rich Text jsoup XSS) FR-11: Quiz (Single/Multiple Choice, True/False, Passing Score, Shuffle, Import Excel) FR-12: Enrollment (ACTIVE/COMPLETED/REFUNDED) FR-13: Progress Tracking (>=90pct video auto-complete, total pct) FR-14: Conditional Review (>=30pct progress or >=3 days anti-fake) FR-15: Comment Q&A (Threaded/Nested parent_id, Instructor label) FR-16: Favorite (toggle heart icon) FR-17: Wishlist (add/remove, auto-remove on enroll) FR-18: Notification (WebSocket/SSE + Email async) FR-19: Certificate (PDF auto UUID S3, /verify-certificate public) FR-20: Report Content (Polymorphic: Course/Comment/User) FR-21: Admin Moderation Dashboard FR-22: Instructor Dashboard (Revenue, Enrollments, Chart) FR-23: Student Dashboard (My Courses, Certificates, History) FR-24: Full-Text Search (PostgreSQL tsvector) FR-25: Multi-Filter (Rating/Level/Price/Sort, AJAX pagination) FR-26: Statistics Reporting (Export Excel)
PHAM VI NGOAI DU AN - OUT-SCOPE
Thanh toan thuc te Stripe/PayPal (chi cau truc du lieu san sang). AI Quiz Generator, AI Chatbot, Recommendation Engine. Mobile App iOS/Android. B2B Subscription Package. Blockchain Certificate Verification. Multi-language i18n.
CONG NGHE SU DUNG
BACKEND: Java 17, Spring Boot 3.x, Spring Security 6, JWT HS256, Spring Data JPA, Hibernate Validator, Bucket4j, jsoup FRONTEND: React 18, TypeScript, Vite, Redux Toolkit, React Router v6, Axios, hls.js, ChartJS/Recharts DATABASE: PostgreSQL 15+ (relational DB, Full-Text Search tsvector), Redis 7.0+ (cache/session/queue) STORAGE: AWS S3, AWS CloudFront CDN, AWS SES VIDEO: FFmpeg HLS 360p/480p/720p/1080p, m3u8 playlist, .ts segments, Redis Queue async DEVOPS: Docker, docker-compose, Ubuntu 22.04 LTS, Nginx SECURITY: BCrypt work factor 12, JWT RTR, RBAC 3 roles, CORS whitelist, Rate Limiting, Signed URLs
CAC STAKEHOLDER
Project Manager / BA: Cao Chi Thien - Quan ly du an, phan tich yeu cau, kiem soat SRS Senior Backend Dev: Nguyen Van Minh - Phat trien API Spring Boot Frontend Developer: Tran Thi Lan - Phat trien UI React/TypeScript Database Engineer: Le Hoang Nam - Thiet ke DB, DevOps, AWS QA Engineer: Pham Thu Ha - Kiem thu toan he thong Nguoi dung cuoi: Guest (khach vang lai), Student (hoc vien), Instructor (giang vien), Admin (quan tri vien)
RUI RO DU AN
R01 CAO: Tien do Backend cham -> Daily standup, uu tien MVP features, scope-freeze sau 09/07 R02 TRUNG BINH: Loi FFmpeg Transcoding -> Test pipeline rieng, fallback direct upload R03 TRUNG BINH: AWS S3/CloudFront sai cau hinh -> Test staging truoc production R04 CAO: CORS/Security misconfiguration -> Security review truoc UAT, pentest noi bo R05 THAP: Database schema conflict -> Flyway/Liquibase migration, code review DB R06 CAO: Timeline 2 tuan qua ngan -> Scope-freeze sau 09/07, khong them tinh nang moi
KET QUA BAN GIAO DU KIEN
1. Source code Backend Spring Boot - GitHub repository 2. Source code Frontend React/TypeScript - GitHub repository 3. Database Schema SQL scripts (PostgreSQL 15 + Migration files) 4. SRS Document (CourseHub_Final_SRS.docx - IEEE 830/29148) 5. API Documentation (Swagger UI tu dong tu Spring Boot annotations) 6. Project Management Documents (Calendar, Template-Technical, Report) 7. Test Cases + Test Report + Postman Collection 8. Deployment Guide (Docker, AWS EC2/RDS/S3/CloudFront setup) 9. He thong da deploy va hoat dong tren server production 10. Bien ban nghiem thu ban giao du an

## 2. Price
BANG CHI PHI DU AN - COURSEHUB ONLINE LEARNING MARKETPLACE
Du an: CourseHub - Online Learning Marketplace |  | Nguoi lap: Cao Chi Thien |  | Tu ngay: 08/07/2026 |  | Den ngay: 21/07/2026
STT | Hang muc | Noi dung mo ta | Ghi chu | So luong | Don vi | Don gia (VND) | Thanh tien (VND)
NHAN SU
1 | NHAN SU | Project Manager / Business Analyst | Cao Chi Thien | 1 | nguoi/2tuan | 15000000 | 15000000
2 | NHAN SU | Senior Backend Developer | Nguyen Van Minh | 1 | nguoi/2tuan | 14000000 | 14000000
3 | NHAN SU | Frontend Developer | Tran Thi Lan | 1 | nguoi/2tuan | 12000000 | 12000000
4 | NHAN SU | Database Engineer / DevOps | Le Hoang Nam | 1 | nguoi/2tuan | 12000000 | 12000000
5 | NHAN SU | QA Engineer | Pham Thu Ha | 1 | nguoi/2tuan | 10000000 | 10000000
HA TANG
6 | HA TANG | AWS EC2 Server t3.medium | Backend server | 1 | instance/thang | 1500000 | 750000
7 | HA TANG | AWS RDS PostgreSQL 15 db.t3.micro | Database server | 1 | instance/thang | 1200000 | 600000
8 | HA TANG | AWS S3 Cloud Storage 50GB | Video PDF Cert | 50 | GB/thang | 24000 | 300000
9 | HA TANG | AWS CloudFront CDN 100GB | HLS video CDN | 100 | GB transfer | 8500 | 212500
10 | HA TANG | Redis Cloud Upstash | Cache and queue | 1 | instance/thang | 200000 | 100000
11 | HA TANG | Domain Name coursehub.com | 1 year | 1 | nam | 300000 | 25000
12 | HA TANG | SSL Certificate Lets Encrypt | HTTPS TLS | 1 | mien phi | 0 | 0
CONG CU
13 | CONG CU | JetBrains IntelliJ IDEA License | Backend IDE | 1 | license/thang | 500000 | 250000
14 | CONG CU | Figma Pro UI Design | UI UX Design | 1 | license/thang | 450000 | 225000
15 | CONG CU | Postman API Testing | API Testing | 1 | mien phi | 0 | 0
16 | CONG CU | AWS SES Email Service | OTP Notif email | 5000 | email | 100 | 100000
17 | CONG CU | FFmpeg Transcoding Worker OSS | Video transcode | 1 | ung dung OSS | 0 | 0
DU PHONG
18 | DU PHONG | Chi phi du phong 5 phan tram | Contingency 5pct | 1 | goi | 0 | 2628125
TONG NGAN SACH DU AN | [6 empty] | 68190625

## 3. Master Plan
KE HOACH TONG THE DU AN - COURSEHUB ONLINE LEARNING MARKETPLACE
Du an: CourseHub - Online Learning Marketplace |  |  | Nguoi lap: Cao Chi Thien |  |  | Start: 08/07/2026 |  |  | End: 21/07/2026
ID | Giai doan | Ten cong viec | Mo ta chi tiet | Phu trach | Phoi hop | FR / Nguon | KH Bat dau | KH Ket thuc | Thoi luong | Phu thuoc | Trang thai | Ket qua
I. KHOI TAO
P01 | I. KHOI TAO | Lap ke hoach tai lieu du an | Project Charter, Master Plan, Price, Nhan su, Bao cao du an | Cao Chi Thien | Toan team |  | 08/07/2026 | 08/07/2026 | 1d |  | Done | Hoan thanh
P02 | I. KHOI TAO | Review va hoan thien SRS | Kiem tra lai SRS, xac nhan pham vi du an FR-01 to FR-26 | Cao Chi Thien | Nguyen Van Minh | FR-01 to FR-26 | 08/07/2026 | 08/07/2026 | 1d |  | Done | Hoan thanh
P03 | I. KHOI TAO | Hoan thien Calendar Template-Technical Report | Dien day du thong tin vao cac file tai lieu du an theo mau | Cao Chi Thien | Toan team |  | 09/07/2026 | 09/07/2026 | 1d | P01,P02 | Done | Hoan thanh
II. THIET KE
D01 | II. THIET KE | Thiet ke kien truc he thong Modular Monolith | API Design, Layer Architecture Controller-Service-Repo, Spring Boot cau hinh ban dau | Nguyen Van Minh | Cao Chi Thien |  | 10/07/2026 | 10/07/2026 | 1d | P03 | Done | Hoan thanh
D02 | II. THIET KE | Thiet ke Database Schema 21 bang | users, roles, user_roles, courses, categories, tags, course_tags, chapters, lessons, lesson_resources, enrollments, progress, reviews, comments, certificates, notifications, reports, course_approval_history, refresh_tokens, instructor_followers, orders | Le Hoang Nam | Nguyen Van Minh | DB Design Sec.8 | 10/07/2026 | 10/07/2026 | 1d | D01 | Done | Hoan thanh
D03 | II. THIET KE | Thiet ke UI/UX Wireframe 14 man hinh | Home, Search, Course Detail, Learning, Dashboard Student/Instructor/Admin, Login, Register, Profile, Course Builder, Certificate, Forgot Password | Tran Thi Lan | Cao Chi Thien | UI Sec.10 | 10/07/2026 | 10/07/2026 | 1d | P03 | Done | Hoan thanh
III. BACKEND
BE01 | III. BACKEND | Setup Spring Boot project cau hinh moi truong | Khoi tao Spring Boot 3.x Java 17, cau hinh PostgreSQL, Redis, Spring Security, Swagger, Docker, env config | Nguyen Van Minh | Le Hoang Nam |  | 11/07/2026 | 11/07/2026 | 1d | D01,D02 | Done | Hoan thanh
BE02 | III. BACKEND | FR-01: Authentication Module | Register OTP Email, Login JWT HS256, Refresh Token Rotation RTR, Logout, Forgot Password, Verify OTP, BCrypt work factor 12 | Nguyen Van Minh |  | FR-01 | 11/07/2026 | 11/07/2026 | 1d | BE01 | Done | Hoan thanh
BE03 | III. BACKEND | FR-02 FR-03: User + Instructor Profile | Update profile avatar bio phone, change password, Become Instructor request, Multi-role Switch Student-Instructor | Nguyen Van Minh |  | FR-02, FR-03 | 11/07/2026 | 11/07/2026 | 1d | BE02 | Done | Hoan thanh
BE04 | III. BACKEND | FR-04 FR-05 FR-06: Course + Category + Tag | Course CRUD lifecycle DRAFT-PENDING-PUBLISHED-ARCHIVED-BLOCKED, Category 3-level hierarchy self-ref, Tag management | Nguyen Van Minh | Le Hoang Nam | FR-04,FR-05,FR-06 | 12/07/2026 | 13/07/2026 | 2d | BE03 | Done | Hoan thanh
BE05 | III. BACKEND | FR-07 FR-08: Chapter + Lesson Management | Chapter CRUD order_index drag-drop, Lesson CRUD VIDEO/PDF/TEXT isPreview config order_index | Nguyen Van Minh |  | FR-07,FR-08 | 12/07/2026 | 13/07/2026 | 2d | BE04 | Done | Hoan thanh
BE06 | III. BACKEND | FR-09 FR-10: Video Processing + Document Resource | S3 Presigned URL, Video upload webhook, Redis Queue Transcoding FFmpeg HLS m3u8 360p-1080p, PDF upload ClamAV, Rich Text jsoup XSS sanitize | Le Hoang Nam | Nguyen Van Minh | FR-09,FR-10 | 14/07/2026 | 14/07/2026 | 1d | BE05 | Done | Hoan thanh
BE07 | III. BACKEND | FR-11: Quiz Module | Quiz CRUD Single/Multiple Choice True/False, Quiz attempts, Passing Score, Shuffle questions/options, Import Excel questions | Nguyen Van Minh |  | FR-11 | 14/07/2026 | 14/07/2026 | 1d | BE05 | Done | Hoan thanh
BE08 | III. BACKEND | FR-12 FR-13: Enrollment + Progress Tracking | Enrollment ACTIVE/COMPLETED/REFUNDED, Progress tracking 90pct video HTML5 event auto-complete, pct total course calculation | Nguyen Van Minh |  | FR-12,FR-13 | 14/07/2026 | 15/07/2026 | 2d | BE06,BE07 | Done | Hoan thanh
BE09 | III. BACKEND | FR-14 FR-15: Review + Comment System | Conditional review 30pct or 3 days anti-fake, Rating avg async update trigger, Threaded comments parent_id, Instructor label Q&A | Nguyen Van Minh |  | FR-14,FR-15 | 15/07/2026 | 15/07/2026 | 1d | BE08 | Done | Hoan thanh
BE10 | III. BACKEND | FR-18 FR-19: Notification + Certificate | Notification in-app WebSocket SSE, Email async queue, Auto Certificate PDF when 100pct progress UUID code S3 storage | Nguyen Van Minh | Le Hoang Nam | FR-18,FR-19 | 15/07/2026 | 15/07/2026 | 1d | BE08 | Done | Hoan thanh
BE11 | III. BACKEND | FR-20 FR-21: Report + Admin Dashboard | Polymorphic Report Course/Comment/User PENDING/RESOLVED/DISMISSED, Admin moderation approve/reject course ban/unban user, Stats MAU CCU | Nguyen Van Minh | Le Hoang Nam | FR-20,FR-21 | 15/07/2026 | 15/07/2026 | 1d | BE09 | Done | Hoan thanh
BE12 | III. BACKEND | FR-22 FR-23 FR-26: Dashboards + Statistics | Instructor Dashboard revenue enrollments chart, Student Dashboard my courses certificates purchase history, Export Excel PDF analytics | Nguyen Van Minh |  | FR-22,FR-23,FR-26 | 15/07/2026 | 15/07/2026 | 1d | BE09,BE10,BE11 | Done | Hoan thanh
BE13 | III. BACKEND | FR-24 FR-25: Full-Text Search + Multi-Filter | PostgreSQL Full-Text Search tsvector, Dynamic Specifications filter rating/level/price/sort, AJAX pagination Pageable Criteria | Nguyen Van Minh |  | FR-24,FR-25 | 15/07/2026 | 15/07/2026 | 1d | BE04 | Done | Hoan thanh
BE14 | III. BACKEND | FR-16 FR-17: Favorite + Wishlist | Toggle favorite heart icon, Wishlist add/remove auto-remove when enrolled, user_favorites wishlists tables | Nguyen Van Minh |  | FR-16,FR-17 | 15/07/2026 | 15/07/2026 | 1d | BE08 | Done | Hoan thanh
IV. FRONTEND
FE01 | IV. FRONTEND | Setup React Vite TypeScript project | Khoi tao Vite/React/TypeScript, cau hinh routing React Router v6, Redux Toolkit, Axios interceptor JWT, UI library | Tran Thi Lan |  |  | 11/07/2026 | 11/07/2026 | 1d | D03 | Done | Hoan thanh
FE02 | IV. FRONTEND | Layout Header Footer Dark Mode Design System | Global CSS variables dark mode toggle responsive breakpoints skeleton loaders toast notifications shared components | Tran Thi Lan |  | UI Sec.10 | 11/07/2026 | 11/07/2026 | 1d | FE01 | Done | Hoan thanh
FE03 | IV. FRONTEND | Login Register OTP Forgot Password pages | Login JWT form, Register 2-step OTP 6-digit auto-focus, Forgot password flow, Zod React Hook Form validation | Tran Thi Lan |  | FR-01 | 12/07/2026 | 12/07/2026 | 1d | FE02 | Done | Hoan thanh
FE04 | IV. FRONTEND | Home Page + Course Listing Search Filter | Hero banner Featured carousel Newest Top instructors, Search sidebar Filter rating/level/price sort AJAX pagination | Tran Thi Lan |  | FR-24,FR-25 | 12/07/2026 | 13/07/2026 | 2d | FE02 | Done | Hoan thanh
FE05 | IV. FRONTEND | Course Detail Page | Breadcrumbs course info instructor profile sticky purchase widget Accordion curriculum reviews section responsive | Tran Thi Lan |  | FR-04,FR-14 | 13/07/2026 | 13/07/2026 | 1d | FE04 | Done | Hoan thanh
FE06 | IV. FRONTEND | Learning Page Video PDF Quiz Text | HLS video player hls.js speed 0.5-2x, PDF viewer, quiz timer form, threaded comments Q and A, progress sidebar Distraction-Free mode | Tran Thi Lan |  | FR-11,FR-12,FR-13,FR-15 | 14/07/2026 | 15/07/2026 | 2d | FE05 | Done | Hoan thanh
FE07 | IV. FRONTEND | Student Dashboard My Courses Certificates History | My Courses grid with progress bars, Certificates tab PDF download share LinkedIn, Purchase history paginated table | Tran Thi Lan |  | FR-19,FR-23 | 15/07/2026 | 15/07/2026 | 1d | FE06 | Done | Hoan thanh
FE08 | IV. FRONTEND | Instructor Dashboard + Course Builder | KPI cards enrollment chart ChartJS, course list by status, Q and A panel, Curriculum Builder drag-drop chapters lessons, video upload progress | Tran Thi Lan |  | FR-04,FR-07,FR-08,FR-09,FR-22 | 15/07/2026 | 16/07/2026 | 2d | FE07 | Done | Hoan thanh
FE09 | IV. FRONTEND | Admin Dashboard Approve Users Reports Categories | KPI system stats, Course approval queue Approve/Reject with reason, User ban/unban, Reports handling, Category Tag management | Tran Thi Lan |  | FR-05,FR-06,FR-20,FR-21 | 16/07/2026 | 16/07/2026 | 1d | FE08 | Done | Hoan thanh
FE10 | IV. FRONTEND | Profile Page Notification Certificate Verify | Profile edit avatar bio phone, change password, notification bell mark-all-read, Certificate display share, /verify-certificate page | Tran Thi Lan |  | FR-02,FR-18,FR-19 | 16/07/2026 | 16/07/2026 | 1d | FE07 | Done | Hoan thanh
V. TICH HOP
INT01 | V. TICH HOP | Tich hop Frontend Backend API | Ket noi toan bo React API calls voi Spring Boot endpoints, xu ly CORS, JWT token interceptor, Axios error handling centralized | Tran Thi Lan | Nguyen Van Minh | All FRs | 16/07/2026 | 17/07/2026 | 2d | BE13,FE09 | Done | Hoan thanh
INT02 | V. TICH HOP | Tich hop AWS S3 + CloudFront CDN | S3 Presigned URL upload, CloudFront CDN distribution, HLS video streaming via CDN, AWS Signed URLs short-lived | Le Hoang Nam | Nguyen Van Minh | FR-09,FR-10 | 17/07/2026 | 17/07/2026 | 1d | BE06 | Done | Hoan thanh
INT03 | V. TICH HOP | Tich hop Email Service + WebSocket Notification | AWS SES Sendgrid email OTP certificate notification, WebSocket SSE real-time notification push Spring Boot | Le Hoang Nam | Nguyen Van Minh | FR-18 | 17/07/2026 | 17/07/2026 | 1d | BE10 | Done | Hoan thanh
VI. KIEM THU
QA01 | VI. KIEM THU | Lap Test Plan + Test Cases 26 FRs | Viet test cases cho 26 FR dua tren SRS Validation Rules Business Rules Boundary Value Analysis Equivalence Partitioning | Pham Thu Ha | Cao Chi Thien | All FRs | 17/07/2026 | 17/07/2026 | 1d | INT01 | Done | Hoan thanh
QA02 | VI. KIEM THU | API Testing Postman Newman | Test toan bo 40+ API endpoints Authentication Course Enrollment Quiz Review Comment Report Certificate Admin moderation | Pham Thu Ha | Nguyen Van Minh | FR-01 to FR-26 | 17/07/2026 | 18/07/2026 | 2d | QA01 | Done | Hoan thanh
QA03 | VI. KIEM THU | Integration UI Testing end-to-end flows | Test luong Register-Enroll-Learn-Quiz-Certificate, Course Create-Submit-Approve-Publish, Admin moderation flows | Pham Thu Ha | Tran Thi Lan | Business Flows | 18/07/2026 | 18/07/2026 | 1d | QA02 | Done | Hoan thanh
QA04 | VI. KIEM THU | Security + Performance Testing | Test JWT RTR CORS Rate Limiting SQL Injection XSS Sanitization, Load test 100 concurrent users Response time check NFR | Pham Thu Ha | Le Hoang Nam | NFR Security Sec.12 | 18/07/2026 | 18/07/2026 | 1d | QA02 | Done | Hoan thanh
VII. TRIEN KHAI
DEP01 | VII. TRIEN KHAI | Cau hinh Docker moi truong Production | Dockerfile cho Spring Boot va React, docker-compose, env variables DB URL JWT Secret S3 credentials Redis URL domain | Le Hoang Nam |  |  | 18/07/2026 | 18/07/2026 | 1d | QA02 | Done | Hoan thanh
DEP02 | VII. TRIEN KHAI | Deploy Backend + Database len server | Deploy Spring Boot tren Ubuntu 22.04, migrate DB schema PostgreSQL 15, cau hinh Redis 7.0, SSL TLS setup Nginx config | Le Hoang Nam | Nguyen Van Minh |  | 18/07/2026 | 19/07/2026 | 2d | DEP01 | Done | Hoan thanh
DEP03 | VII. TRIEN KHAI | Deploy Frontend + cau hinh CDN | Build React Vite production bundle, deploy len S3/Nginx, cau hinh CloudFront CDN, HTTPS TLS, domain DNS setup | Le Hoang Nam | Tran Thi Lan |  | 19/07/2026 | 19/07/2026 | 1d | DEP02 | Done | Hoan thanh
VIII. KET THUC
UAT01 | VIII. KET THUC | User Acceptance Testing UAT | Kiem tra end-to-end theo kich ban nghiem thu: Guest Student Instructor Admin flows theo yeu cau SRS | Pham Thu Ha | Cao Chi Thien | All FRs | 20/07/2026 | 20/07/2026 | 1d | DEP03 | Done | Hoan thanh
UAT02 | VIII. KET THUC | Bug Fix sau UAT | Sua cac loi phat hien trong UAT, retest va dong cac ticket loi, cap nhat defect tracker | Nguyen Van Minh | Tran Thi Lan, Pham Thu Ha |  | 20/07/2026 | 21/07/2026 | 2d | UAT01 | Done | Hoan thanh
CL01 | VIII. KET THUC | Hoan thien tai lieu cuoi du an | Cap nhat SRS final, API documentation Swagger, huong dan van hanh he thong, ban giao source code GitHub | Cao Chi Thien | Toan team |  | 21/07/2026 | 21/07/2026 | 1d | UAT02 | Done | Hoan thanh
CL02 | VIII. KET THUC | Nghiem thu va Ban giao du an | Hop tong ket, ky bien ban nghiem thu, ban giao toan bo san pham va tai lieu du an CourseHub | Cao Chi Thien | Toan team |  | 21/07/2026 | 21/07/2026 | 1d | CL01 | Done | Hoan thanh

## 4. Nhan su du an
DANH SACH NHAN SU THAM GIA DU AN COURSEHUB
STT | Ho Ten | Don vi | Chuc vu DA | Vai tro | Ky nang chinh | Cong viec phu trach | Dien thoai | Email
1 | Cao Chi Thien | CourseHub Team | Giam doc du an / BA | Project Manager / Business Analyst | Project Management, Business Analysis, SRS, Risk Management | Quan ly tien do, Phan tich yeu cau, Kiem soat SRS, Bao cao du an | 0901234567 | thiencc@coursehub.com
2 | Nguyen Van Minh | CourseHub Team | Backend Developer | Senior Backend Developer | Java 17, Spring Boot 3.x, Spring Security, JWT, Redis, PostgreSQL | Authentication, Course API, Enrollment, Quiz, Notification Service | 0902345678 | minhnguyenv@coursehub.com
3 | Tran Thi Lan | CourseHub Team | Frontend Developer | Frontend Developer | React 18, TypeScript, Vite, Redux, hls.js, ChartJS | UI/UX Components, Learning Page, Dashboard, Search Filter, Certificate | 0903456789 | lantran@coursehub.com
4 | Le Hoang Nam | CourseHub Team | Database Engineer | Database Engineer / DevOps | PostgreSQL 15, Redis 7, Docker, AWS S3, CloudFront, FFmpeg | Database Design, Schema Migration, AWS Integration, Deployment, DevOps | 0904567890 | namle@coursehub.com
5 | Pham Thu Ha | CourseHub Team | QA Engineer | QA Engineer | Test Case Design, Postman Newman, Manual Testing, Bug Reporting | Test Plan, Test Cases, API Testing, UAT Execution, Bug Tracking | 0905678901 | hapham@coursehub.com
CHI TIET PHAN CONG CONG VIEC THEO TUNG THANH VIEN
Thanh vien | FR / Task ID | Giai doan | Ngay Bat dau | Ngay Ket thuc | Ten cong viec
Cao Chi Thien |  | I. KHOI TAO | 08/07/2026 | 08/07/2026 | Lap ke hoach tai lieu du an
Cao Chi Thien | FR-01 to FR-26 | I. KHOI TAO | 08/07/2026 | 08/07/2026 | Review va hoan thien SRS
Cao Chi Thien |  | I. KHOI TAO | 09/07/2026 | 09/07/2026 | Hoan thien Calendar Template-Technical Report
Nguyen Van Minh |  | II. THIET KE | 10/07/2026 | 10/07/2026 | Thiet ke kien truc he thong Modular Monolith
Le Hoang Nam | DB Design Sec.8 | II. THIET KE | 10/07/2026 | 10/07/2026 | Thiet ke Database Schema 21 bang
Tran Thi Lan | UI Sec.10 | II. THIET KE | 10/07/2026 | 10/07/2026 | Thiet ke UI/UX Wireframe 14 man hinh
Nguyen Van Minh |  | III. BACKEND | 11/07/2026 | 11/07/2026 | Setup Spring Boot project cau hinh moi truong
Nguyen Van Minh | FR-01 | III. BACKEND | 11/07/2026 | 11/07/2026 | FR-01: Authentication Module
Nguyen Van Minh | FR-02, FR-03 | III. BACKEND | 11/07/2026 | 11/07/2026 | FR-02 FR-03: User + Instructor Profile
Nguyen Van Minh | FR-04,FR-05,FR-06 | III. BACKEND | 12/07/2026 | 13/07/2026 | FR-04 FR-05 FR-06: Course + Category + Tag
Nguyen Van Minh | FR-07,FR-08 | III. BACKEND | 12/07/2026 | 13/07/2026 | FR-07 FR-08: Chapter + Lesson Management
Le Hoang Nam | FR-09,FR-10 | III. BACKEND | 14/07/2026 | 14/07/2026 | FR-09 FR-10: Video Processing + Document Resource
Nguyen Van Minh | FR-11 | III. BACKEND | 14/07/2026 | 14/07/2026 | FR-11: Quiz Module
Nguyen Van Minh | FR-12,FR-13 | III. BACKEND | 14/07/2026 | 15/07/2026 | FR-12 FR-13: Enrollment + Progress Tracking
Nguyen Van Minh | FR-14,FR-15 | III. BACKEND | 15/07/2026 | 15/07/2026 | FR-14 FR-15: Review + Comment System
Nguyen Van Minh | FR-18,FR-19 | III. BACKEND | 15/07/2026 | 15/07/2026 | FR-18 FR-19: Notification + Certificate
Nguyen Van Minh | FR-20,FR-21 | III. BACKEND | 15/07/2026 | 15/07/2026 | FR-20 FR-21: Report + Admin Dashboard
Nguyen Van Minh | FR-22,FR-23,FR-26 | III. BACKEND | 15/07/2026 | 15/07/2026 | FR-22 FR-23 FR-26: Dashboards + Statistics
Nguyen Van Minh | FR-24,FR-25 | III. BACKEND | 15/07/2026 | 15/07/2026 | FR-24 FR-25: Full-Text Search + Multi-Filter
Nguyen Van Minh | FR-16,FR-17 | III. BACKEND | 15/07/2026 | 15/07/2026 | FR-16 FR-17: Favorite + Wishlist
Tran Thi Lan |  | IV. FRONTEND | 11/07/2026 | 11/07/2026 | Setup React Vite TypeScript project
Tran Thi Lan | UI Sec.10 | IV. FRONTEND | 11/07/2026 | 11/07/2026 | Layout Header Footer Dark Mode Design System
Tran Thi Lan | FR-01 | IV. FRONTEND | 12/07/2026 | 12/07/2026 | Login Register OTP Forgot Password pages
Tran Thi Lan | FR-24,FR-25 | IV. FRONTEND | 12/07/2026 | 13/07/2026 | Home Page + Course Listing Search Filter
Tran Thi Lan | FR-04,FR-14 | IV. FRONTEND | 13/07/2026 | 13/07/2026 | Course Detail Page
Tran Thi Lan | FR-11,FR-12,FR-13,FR-15 | IV. FRONTEND | 14/07/2026 | 15/07/2026 | Learning Page Video PDF Quiz Text
Tran Thi Lan | FR-19,FR-23 | IV. FRONTEND | 15/07/2026 | 15/07/2026 | Student Dashboard My Courses Certificates History
Tran Thi Lan | FR-04,FR-07,FR-08,FR-09,FR-22 | IV. FRONTEND | 15/07/2026 | 16/07/2026 | Instructor Dashboard + Course Builder
Tran Thi Lan | FR-05,FR-06,FR-20,FR-21 | IV. FRONTEND | 16/07/2026 | 16/07/2026 | Admin Dashboard Approve Users Reports Categories
Tran Thi Lan | FR-02,FR-18,FR-19 | IV. FRONTEND | 16/07/2026 | 16/07/2026 | Profile Page Notification Certificate Verify
Tran Thi Lan | All FRs | V. TICH HOP | 16/07/2026 | 17/07/2026 | Tich hop Frontend Backend API
Le Hoang Nam | FR-09,FR-10 | V. TICH HOP | 17/07/2026 | 17/07/2026 | Tich hop AWS S3 + CloudFront CDN
Le Hoang Nam | FR-18 | V. TICH HOP | 17/07/2026 | 17/07/2026 | Tich hop Email Service + WebSocket Notification
Pham Thu Ha | All FRs | VI. KIEM THU | 17/07/2026 | 17/07/2026 | Lap Test Plan + Test Cases 26 FRs
Pham Thu Ha | FR-01 to FR-26 | VI. KIEM THU | 17/07/2026 | 18/07/2026 | API Testing Postman Newman
Pham Thu Ha | Business Flows | VI. KIEM THU | 18/07/2026 | 18/07/2026 | Integration UI Testing end-to-end flows
Pham Thu Ha | NFR Security Sec.12 | VI. KIEM THU | 18/07/2026 | 18/07/2026 | Security + Performance Testing
Le Hoang Nam |  | VII. TRIEN KHAI | 18/07/2026 | 18/07/2026 | Cau hinh Docker moi truong Production
Le Hoang Nam |  | VII. TRIEN KHAI | 18/07/2026 | 19/07/2026 | Deploy Backend + Database len server
Le Hoang Nam |  | VII. TRIEN KHAI | 19/07/2026 | 19/07/2026 | Deploy Frontend + cau hinh CDN
Pham Thu Ha | All FRs | VIII. KET THUC | 20/07/2026 | 20/07/2026 | User Acceptance Testing UAT
Nguyen Van Minh |  | VIII. KET THUC | 20/07/2026 | 21/07/2026 | Bug Fix sau UAT
Cao Chi Thien |  | VIII. KET THUC | 21/07/2026 | 21/07/2026 | Hoan thien tai lieu cuoi du an
Cao Chi Thien |  | VIII. KET THUC | 21/07/2026 | 21/07/2026 | Nghiem thu va Ban giao du an